## Gaint Chart
Final Project Task
| Start Date 7/6/2021 | Week First
* | Tasks | Week Days
1 | Project Planing | Wednesday |  | 6.5 Hour
2 | Look For Project | Thursday | 7.5 Hour |  | Total Hours = 31.5
3 | Thniking About Topic | Friday |  | 7.5 Hour
4 | Resarch Information | Saturday | 10 hour
Sunday
Monday
| End Date 9/6/2021 | Tuesday
* | Review | Week Second
| Start Date 14/6/2021 | Week Days
1 | Give feedback about Research | Wednesday |  | 6 Hour
2 | Result | Thursday | 7 hour
3 | Final Pick one Topic | Friday |  | 7 hour
4 | Plain Layouts | Saturday |  |  | Total Hour = 40
5 | Start Working On Layouts | Sunday | 10 Hour
6 | Plain Models | Monday |  | 10 Hor
7 | Start Making Models | Tuesday
8 | Start Making Classes
End Date 20/6/2021
* | Working on Database,Testing, Add Templete, Activities | Week Third
| Start Date = 21/6/2021 | Week Days
1 | Working on Database and Testing | Wednesday |  | 5 Hour
2 | Working On Activities | Thursday | 7 Hour |  | Total Hour = 39
3 | Choose Templete and Start Working on Templete | Friday |  | 7 Hour
4 | Change the designing and add some Images | Saturday | 10 Hour
5 | In the last Project Ready and Review all Project | Sunday |  | 10 Hour
6 | Final Working On documentation | Monday
| End date = 25/6/2021 | Tuesday

## Usability Testing
MVC Project Testing
| Questions |  | Answer Scale
| Usability and Acessability | 70 % Agree | 70% Disagree | 100% Agree | 100 % Disagree | Average
1 | Project is Running very fast on Website |  |  | 100 % Agree
2 | Firstly Home Page will Open while Project Run |  |  | 100 % Agree
3 | Login Page Working Correctly |  |  | 100 % Agree
4 | Register Page Working Correctly |  |  | 100 % Agree
Functionality
1 | All the Pages Run Correctly |  |  | 100 % Agree
2 | All the Buttons Work Correctly |  |  | 100 % Agree
3 | Crud Operation Run Fantastic |  |  | 100 % Agree
Understandability
1 | Coding is very easy to read |  |  | 100 % Agree
2 | Migration is very easy to add |  |  | 100 % Agree
3 | Project is Build very Fast |  |  | 100 % Agree
Main Motive for Booking
1 | This Project is suitable for booking seats in threater |  |  | 100 % Agree
2 | The Main Target in this project for audience booking |  |  | 100 % Agree
3 | You can choose any show with easy way |  |  | 100 % Agree

## MVC Project Testing
MVC Project Testing
Number | Pages Details |  | Excepted Opinion | Actual Opinion | Successful/Unsuccessful/Issues
1 | Home Page | = | Home Page Displayed | Home Page images and design Displayed | Successful
2 | Login Page | = | Login Page Displayed | Options Clickable | Successful
3 | Register Page | = | Register Page Displayed | Options Clickable | Successful
4 | Manage Account | = | Manage Account Displayed | Options Clickable | Successful
5 | Show Page | = | Show Page displayed | Buttions displayed | Successful
6 | Performance Page | = | Performance Page Displayed | Buttons Displayed | Successful
7 | Seat Page | = | Seat Page Displayed | Buttons Displayed | Successful
8 | Booking Page | = | Booking Page Displayed | Buttons Displayed | Successful
Responsiveness Desgin
1 | Home Page |  |  |  | Successful
2 | Login Page |  |  |  | Successful
3 | Register Page |  |  |  | Successful
4 | Show Page |  |  |  | Successful
5 | Performance |  |  |  | Successful
6 | Booking |  |  |  | Successful
7 | Seat Page |  |  |  | Successful